## Form Responses 1
Timestamp | Name | SAP ID | Project | Role In Project | 1. What was the final status of your project? | 2. If the project was delayed or incomplete, what was the primary reason? | 3. At which stage did your team face the most issues? | What kind of challenges did you observe during the project? (Select all that apply) | 6. In hindsight, which of the following would have improved your project success? (Select all that apply) | 7. Did your team conduct regular reviews or stand-ups during the project? | 8. How early did you start facing project risks? | 9. Were any risk mitigation strategies used? | 10. Would you approach the project differently if you could start again?
2025-04-20 20:10 | Amulya Jain | 500122439 | CtrlX-Error | Full Stack and Project Management lead | Partially completed | Poor time management | Testing and debugging | Inadequate technical knowledge, Dependency on unavailable tools/tech, Lack of commitment or accountability, Poor communication | Better time planning, Stronger technical mentorship | Yes, regularly | Midway through | Yes, and they worked | Yes, with some changes
2025-04-26 09:48 | Soumya Jain | 500119436 | CtrlX-Error | Frontend and UX | Completed but with major compromises | Technical difficulties | Testing and debugging | Inadequate technical knowledge, Dependency on unavailable tools/tech, Lack of commitment or accountability | Better time planning, Use of project management tools, Stronger technical mentorship | Yes, regularly | Toward the end | Yes, and they worked | Yes, with some changes
2025-04-26 09:50 | Naman Chanana | 500119485 | Ctrl X Error | Backend developer | Partially completed | Poor time management | Testing and debugging | Inadequate technical knowledge, Dependency on unavailable tools/tech | Better time planning, Stronger technical mentorship | Yes, regularly | Midway through | Yes, and they worked | Yes, with some changes
2025-04-26 10:07 | Smriti Walia | 500124833 | Ctrl_X Error: Empowering Teams with Smart Bug Tracking | Testing, UI and Research | Successfully completed as planned | Unclear requirements or frequent changes | Implementation/coding | Dependency on unavailable tools/tech | More realistic goal setting | Yes, regularly | Midway through | Yes, and they worked | No, we did our best